## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2175-swen-261-01-d TheAdoptedFive
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  | Moved Under Signout Story (TBA) |  |  |  | C.A. M.A.
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A.
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). |  | JA - 2/28/18 - Pass |  |  |  | C.A. M.A. - Does not accurately display number of active players on home page (signed out version)
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  | JA - 2/28/18 - Pass |  | JA - 3/29/18 |  | C.A. M.A.
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting White player and my opponent as the Red player. |  | JA - 2/28/18 - Pass |  | JA - 3/29/18 |  | C.A. M.A.
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  | Not Implemented |  | JA - 3/29/18 |  | C.A. M.A.
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  | Not Implemented |  | JA - 3/29/18 |  | C.A. M.A.
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  | JA - 2/28/18 - Ajax not implemented, recognizes attempt, Pass? |  | JA - 3/29/18 |  | C.A. M.A.
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  | JA - 2/28/18 - Ajax not implemented, Pass? |  | JA - 3/29/18 |  | C.A. M.A.
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  | JA - 2/28/18 - Ajax not implemented, Pass? |  | JA - 3/29/18 |  | C.A. M.A.
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  | JA - 2/28/18 - Ajax not implemented, Pass? |  | JA - 3/29/18 |  | C.A. M.A.
As a player I want to have a piece so that it can represent me on the board. | Given I am a player, when I enter the game then I should have some sort of graphics pieces assigned to me. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given I am a player, when I start a game then my pieces should have a color to distinguish mine from those of my opponent. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
As a Player I want to experience no internal errors so that I can have a smooth playing experience. | Given that I have a valid name when I try to play a game then the game should run smoothly without server errors. |  |  |  | JA - 3/29/18 - For current implementation |  | C.A. M.A.
| Given that I have started a game when I am ready to play then no links/actions within the game can cause a crash. |  |  |  | JA - 3/29/18 |  | C.A. M.A. - This is a general mention of not having anything be able to crash the program. However, resignation is the only thing that seems to cause issues. If a player resigns the opposing player's game crashes.
As a Player I want to sign-out so that I can leave the session. | Given that I _have_ signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given that I have signed out when other players try to sign in then my name must be available. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given that I have signed out when other players try to start a game I must not be in the listed of available players. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given that I am a player when I sign out I should be returned to the Home page, as it appears for players who haven't signed in. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
As a Player, I want to be able to see my pieces with correct coloring and positioning so that it follows the rules of checkers. | Given I am a player when I see the board then my are pieces orientated properly |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given I am a player when I start the game then the pieces are in their positions conforming to the rules. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given I am a player, when I start a game the board and pieces should be displayed according to my perspective, with my pieces initialized on the bottom three rows of the board as it appears on my display. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
As a player I want to be able to move my basic piece(s) so I can proceed with a game of checkers. | Given I am a player when when I determine a capture then I should be able to jump the captured piece. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given I am a player when when i select my basic piece in a multiple jump situation then I should be able to perform that multi-jump. |  |  |  | JA - 3/29/18 |  | C.A. M.A. - On the second part of a double jump, if a player attempts to backup on the move an ajax error is thrown.
| Given I am able to capture a piece at the start of my turn, when it is my turn then I must be only be allowed to make capture moves during this turn. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given a basic piece, when it is my turn then I should be able to move it one square diagonally toward my opponent's side of the board. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given there are two or more pieces on the board, when it is my turn then I should not be able to move one of my pieces into a space already occupied by a different piece. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
| Given I am playing a game of checkers, when it is my turn then I should be able to move one of my pieces on the board. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
Given I am a player, when there is at least one capture move available to me, I should be forced to make one of these moves.
Given I am a player, when I make the first jump in an available multi-jump, then I should be forced to complete the multi-jump.
Given I am a player, when it is my turn if I have moved a piece but not submitted my turn, I should be able to undo the move and choose another available move.
| Given I am playing a game of checkers, when either player finishes their turn, then my board should update to the new configuration. |  |  |  | JA - 3/29/18 |  | C.A. M.A.
As a player I want to be able to move my king piece so I can further play the game. | Given I am a player when when I select my king piece then it must still have the same functionality of a basic piece, plus additional features. | [5 empty] | C.A. M.A.
| Given I am a player when when i select my king piece then then I can move it based on the defined rules of checker. | [5 empty] | C.A. M.A.
As a PLAYER I want to BE ABLE TO LEAVE so that I CAN EXIT A BAD GAME. | Given that I would like to leave and end the game when I use the quit option then I expect to have left the game. | [5 empty] | C.A. M.A. - Resign still causes issues for the player who did not click the resign button.
Given that I have left the game when I leave the game then I expect that the other player was informed and won the game.
Given I am a player, when I sign out during a game then my opponent should be notified that I forfeited and I should be signed out and returned to the home screen as usual.
As a player I want to win a game by capturing all of my opponent's pieces, or lose by having all of my pieces captured, so I can leave the match and return to the home page. | Given I am a player when a player has no more pieces, then the I should be notified who won and allowed to return to the home page.
Given I am a player, when the game is over then I should not be able to move any pieces or forfeit the match.
As a spectator I want to be able to view an ongoing game so I can watch other players and learn. | Given I am not in a game when I would like to view a game then I can find a game to view.
Given I am a spectator when I am viewing a game then I should not be able to interact or influence the game at all.
Given I am a spectator when I am viewing an ongoing game then I should see the game progress in real-time.
As a player I want to be able to receive help (rules/suggestions) so I can do well in the game. | **Given** I am a confused player **when** I am playing the game **then** I should see a list of rules if I select Help.
Given I am unfamiliar with checkers, when it is my turn then I should see a selection of move options for my current turn.